## Sheet1
Task Name | Duration | Start date | End date
Sprint Meeting
Sprint Meeting 01 | 1 day | 2023-10-08
Sprint Meeting 02 | 1 day | 2023-10-20
Sprint Meeting 03 | 1 day | 2023-11-21
Sprint Meeting 04 | 1 day | 2023-01-20
Sprint Meeting 05 | 1 day | 2023-02-13
Sprint Meeting 06 | 1 day | 2023-02-27
Sprint Meeting 07 | 1 day | 2023-03-06
Sprint Meeting 08 | 1 day | 2023-03-20
Sprint Meeting 09 | 1 day | 2023-04-03
Sprint Meeting 10 | 1 day | 2023-04-20
Requirement Analysis
Requirement Gathering | 8 days | 2023-10-12 | 2023-10-20
Requirement Analyzing | 15 days | 2023-10-20 | 2023-11-05
Requirement Finalizing
Milestone 1
Planning And Designing
Design UML Diagrams | 16 days | 2023-11-06 | 2023-11-21
Design ER Diagrams | 16 days | 2023-11-06 | 2023-11-21
Design UI/UX | 7 days | 2023-01-11 | 2023-01-18
Design the techstack | 2 days | 2023-01-19 | 2023-01-20
Milestone 2
Implimentation
Coding | 58 days | 2023-02-01 | 2023-03-30
Code Reviewing | 58 days | 2023-02-01 | 2023-03-30
Milestone 3
Testing
Unit testing | 5 days | 2023-04-01 | 2023-04-05
Quality Assuarance | 6 days | 2023-04-05 | 2023-04-10
Milestone 4
Deployment
Buy Domain | 2 days | 2023-04-17 | 2023-04-18
Hosting | 2 days | 2023-04-19 | 2023-04-20
Milestone 5
Maintenance